## Introduction
Serial No. N7324 NAFO SCS Doc. 22/20
SCIENTIFIC COUNCIL MEETING - 2022
Scientific Council 5-Year Work Plan 2022
This plan was developed in response to Commisison Request # 10 in 2020 (COM Doc. 20-16): The Commission requests the Scientific Council to continue to develop a 3-5 year work plan, which reflects requests arising from the 2020 Annual Meeting, other multi-year stock assessments and other scientific inquiries already planned for the near future. The work plan should identify what resources are necessary to successfully address these issues, gaps in current resources to meet those needs and proposed prioritization by the Scientific Council of upcoming work based on those gaps. Work on the plan plan commenced in 2019 in response to Commisison Request # 16 (COM Doc. 18-20) and continued during SC meetings in 2020 and 2021. The 5-year plan allows for a high-level view of activities planned for the next five years, with more detailed annual plans for each year in which resource gaps and priorities are addressed. The plan includes requests from the Commission, including stock assessments, other scientific inquiries (e.g. from specific contracting parties for straddling stocks) and SC work and advice of its own accord. SC will update and review the plan each June and September to include all requests with prioritization and rationale where appropriate as well as the resources required to respond to the requests.
The SC notes that in the next two to three years the revision of two Management Strategies (redfish Div. 3LN and Greenland halibut Sub 2 Div. 3KLMNO) and the PAF revision coincide in time and, given the complexity and the high level of SC resources/capacity required to complete these tasks, SC strongly recommends against attempting to perform all three concurrently. Since the PA review is already underway and involves partipication of external experts, SC recommends prioritizing one of the Mangement Strategy reviions to commence first with the other being postponed to a later date. Provisional work plans for both MS revisions are included in the detailed work plan for 2022, but it is not expected that both will be carried out concurrently.
Northwest Atlantic Fisheries Organization
1601 Lower Water Street, Suite 401
Halifax, Nova Scotia, B3J 3P6 CANADA
Tel: 902-468-5590
E-mail: info@nafo.int

## 5-year
Road map component | Commission Request | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Stock Assessment | Request #1. The Commission requests that the Scientific Council provide advice for the management of the fish stocks below according to the assessment frequency presented below. * including coastal state requests | June meeting: 27 May-11 June 2021 | June meeting: 3-16 June 2022 | June meeting: 2023 | June meeting: 2024 | June meeting: 2025 | June meeting: 2026
(STACFIS items) Full assessments
3M Cod |  | 1. 3M Cod | 3M Cod | 3M Cod | 3M Cod | 3M Cod | 3M Cod
3M Redfish |  | 2. 3M Redfish |  | 3M Redfish |  | 3M Redfish
3LNO Thorny skate |  |  | 3LNO Thorny skate |  | 3LNO Thorny skate |  | 3LNO Thorny skate
3NO Witch flounder |  |  | 3NO Witch flounder |  | 3NO Witch flounder
3LN Redfish |  |  | 3LN Redfish |  | 3LN Redfish |  | 3LN Redfish
3NO White hake |  | 3. 3NO White hake |  | 3NO White hake |  | 3NO White hake
3LNO American plaice |  | 4. 3LNO American plaice |  |  | 3LNO American plaice (benchmark in spring?)
3M American plaice |  |  |  | 3M American plaice |  |  | 3M American plaice
3NO Capelin *IMRs until there is a survey |  | 5. 3NO Capelin |  |  | *3NO Capelin will not be assessed, IMR only
SA 3+4 Northern shortfin squid |  |  | SA 3+4 Northern shortfin squid |  |  | SA 3+4 Northern shortfin squid
3O Redfish |  |  | 3O Redfish |  |  | 3O Redfish
3LNO Yellowtail flounder |  | 6. 3LNO Yellowtail flounder |  |  | 3LNO Yellowtail flounder
3NO Cod |  | 7. 3NO Cod |  |  | 3NO cod (benchmark in spring?)
SA 2 + 3KLMNO Greenland halibut |  |  | SA2 + 3KLMNO Greenland halibut |  | SA2+3KLMNO Greenland halibut (unless MSE is complete) |  | SA2 + 3KLMNO Greenland halibut
Sub Area 1: |  | Sub Area 1: | Sub Area 1: | Sub Area 1: | Sub Area 1: | Sub Area 1: | Sub Area 1:
Golden redfish |  |  |  | Golden redfish |  |  | Golden redfish
Demersal deep-sea redfish |  |  |  | Demersal deep-sea redfish |  |  | Demersal deep-sea redfish
Atlantic wolffish |  |  |  | Atlantic wolffish |  |  | Atlantic wolffish
Spotted wolfish |  |  |  | Spotted wolfish |  |  | Spotted wolfish
SA 0 and 1 Greenland halibut |  |  | SA 0 and 1 Greenland halibut |  | SA 0 and 1 Greenland halibut |  | SA 0 and 1 Greenland halibut
Greenland halibut SA1 inshore |  |  | Greenland halibut SA1 inshore |  | Greenland halibut SA1 inshore |  | Greenland halibut SA1 inshore
NIPAG: |  | NIPAG meeting: | NIPAG meeting: (September) | NIPAG meeting: (September) | NIPAG meeting: (September) | NIPAG meeting: (September) | NIPAG meeting: (September)
3M Northern shrimp |  | 6. 3M Northern shrimp | 3M Northern shrimp | 3M Northern shrimp | 3M Northern shrimp | 3M Northern shrimp | 3M Northern shrimp
3LNO Northen shrimp |  | 3LNO Northen shrimp |  | 3LNO Northen shrimp |  | 3LNO Northen shrimp
Northern shrimp in Denmark Strait |  | 7. Northern shrimp in Denmark Strait | Northern shrimp in Denmark Strait | Northern shrimp in Denmark Strait | Northern shrimp in Denmark Strait | Northern shrimp in Denmark Strait | Northern shrimp in Denmark Strait
Northern shrimp in SA 0 and 1 |  | 8. Northern shrimp in SA 0 and 1 | Northern shrimp in SA 0 and 1 | Northern shrimp in SA 0 and 1 | Northern shrimp in SA 0 and 1 | Northern shrimp in SA 0 and 1 | Northern shrimp in SA 0 and 1
Other stocks without fixed assessment frequency:
Roughhead grenadier
Splendid Alfonsino |  |  | Splendid alfonsino
Capelin (IMRs only for now)
| Request # 10 The Commission requests that any new results from stock assessments and the scientific advice of Cod 2J3KL (Canada), Witch 2J3KL (Canada) and Pelagic Sebastes mentella (ICES Divisions V, XII and XIV; NAFO 1) to be presented to the Scientific Council and request the Scientific Council to prepare a summary of these assessments to be included in its annual report. |  | Assessments for these domestically assessed stocks have been presented in the last couple years. In 2022 there was no Northern cod assessment as a key survey had been cancelled. The latest assessment for witch flounder was presented. The stock shows some improvement but remains below the Canadian Blim. The 2021 ICES assessment for Pelagic sebastes mentella was presented and the results showed that both the shallow and deep stocks are well below Blim.
| Request #9: The Commission requests that Scientific Council do a full assessment for Div. 3LN redfish and provide advice based on the projection for various harvest levels for two-years (2023 and 2024) to evaluate the impacts according to the performance statistics from NAFO CEM Annex I.H. |  | The updated ASPIC model was not accepted by STACFIS and as such, the stock status is currently unknown. The mean of the standardized survey timeseries indicates aggregate biomass is at the long-term mean. An interim limit reference point was adopted as this stock will be undergoing an MSE.
Stock management (HCR's and PA framework) (RBMS items) | Request #4. Scientific Council initiate the first steps in both the 2+3KLMNO Greenland halibut and 3LN redfish MSE processes during 2021-2022, namely: a. Compile catch and survey data and any additional sources of information used in the current models; b. Review and finalize the data inputs for review at the June 2022 Scientific Council meeting when conducting both the 3LN redfish assessment and the assessment of Greenland Halibut Exceptional Circumstances/ Provision of TAC advice c. Time permitting, further work on the respective MSE work plans by the SC-GHL and SC-Redfish subgroups for presentation to WG-RBMS or SC. | 3LN redfish HCR no decision required for 2022. Scoping exercise for MSE (request #11) | 3LN redfish HCR MSE and HCR currently required for 2023 decision (redfish assessment required) Greenland Halibut HCR MSE and HCR currently required for 2023 decision (redfish assessment required) | 3LN redfish HCR Recommend MSE and HCR to Commission for 2024 decision - this timeline has been removed and is more likely a year later at this time. Greenland Halibut HCR Recommend MSE and HCR to Commission for 2023 decision - this timeline has been removed and is more likely a year later at this time. | 3LN redfish HCR 1) Calculate HCR and examine ECs * MSE work is likely delayed and the MSE work will continue Greenland Halibut HCR 1) Calculate HCR and examine ECs * MSE work is likely delayed and the MSE work will continue | 3LN redfish HCR 1) Calculate HCR * MSE work is likely delayed and the MSE work will continue in 2025 | 3LN redfish HCR 1) Calculate HCR
| Request #2: The Commission requests the Scientific Council to monitor the status of Greenland halibut. Conditional on the absence of other reasons for Exceptional Circumstances arising (other than the missing Canadian spring 3LNO survey), to calculate in 2022 the HCR adjusting the TAC advised for 2022 using four survey indices (Canadian fall 2J3K, Canadian fall 3LNO, EU 3M 0-1400m, and EU-Spain 3NO surveys) to provide TAC advice for 2023. If other reasons for exceptional circumstances are occurring, the EC protocol will provide guidance on what steps should be taken. | Greenland Halibut (2+Div 3KLMNO) HCR’s 1) Monitor stock status to compute TAC using HCR 2) Determine whether there are exceptional circumstances | Request #2: Greenland Halibut (2+Div 3KLMNO) HCR’s Request #2: Greenland Halibut (2+Div 3KLMNO) HCR’s 1) Monitor stock status to compute TAC using HCR (complete) 2) Determine how to handle identified exceptional circumstances (complete) Exceptional circumstances were triggered because of missing surveys and analyses were carried out to see if TAC could still be calculated with the available information. The conclusion was yes (the tAC was not very sensitive to leaving out spring 3LNO so the TAC for 2023 was calculated)
| Request #7 : The Commission requests the Scientific Council to continue progression on the review of the NAFO PA Framework in accordance to the PAF review work plan approved in 2020 (NAFO COM-SC Doc. 20-04). | PA framework · Progress on the review of the NAFO PA Framework. | PA framework "Next Steps" (after mapping execise was reviewed by SC in June 2021) -Action 1 – Mapping exercise to be reviewed by RBMS August 2021 -Action 2 - Structural aspects and quantification of uncertainty and risk by September 2022 -Action 3: Workshop with scientists and managers, ~March 2022, to address the ToR 1 and propose of revision of the NAFO PAF to be reviewed by RBMS. -Action 4: The proposed NAFO PAF will be presented to SC and WG-RBMS and the Commission in June, August and September respectively in 2022. -Action 5: Workshop -with scientists and managers after Sept 2022, to develop the guidelines to support the implementation of the proposed NAFO PA framework. Guidelines to be completed by end of 2022. | The timelines have been delayed so the PA review is likely to be ongoing in 2023
Habitat Impact assessment (WG EFFM VME work) | Request # 3: The Commission requests that the Scientific Council continue its evaluation of the impact of scientific trawl surveys on VME in closed areas, and the effect of excluding surveys from these areas on stock assessments. | This is almost complete, results from EU surveys to be presented at SC in September. WG-ESA needs to address possible alternative methods to assess changes in VME biomass inside closures to consider potential recoveries. | Initial work is complete complete. Request is ongoing a a finer scale examination is required to potentially survey a subset of the area. WG-ESA needs to address possible alternative methods to assess changes in VME biomass inside closures to consider potential recoveries.
| Request #6: The Commission requests that SC , in preparation of the re-assessment of NAFO bottom fisheries in 2021 and discussion on VME fishery closures: i. Assess the overlap of NAFO fisheries with VME to evaluate fishery specific impacts in addition to the cumulative impacts for NRA fisheries; ii. Consider clearer objective ranking processes and options for weighting criteria for the overall assessment of significant adverse impacts and the risk of future adverse impacts; iii. Maintain efforts to assess all six FAO criteria including the three FAO functional SAI criteria which could not be evaluated in the current assessment. iv. Provide input and analysis of potential management options, with the goal of supporting meaningful and effective discussions between scientists and managers at the 2021 WG-EAFFM meeting; (includes a revision to seamount closure boundaries proposed in 2020) v. Continue to work on the VME indicator species as listed in Annex IE, Section VI to prepare for the next assessment. | The re-assessment will be complete as of June 2021 but there will be work required to prepare for the next re-assessment. More work is required for point iii on SAI criteria, including standardizing benthic biomass data across surveys and evaluating the significance of NAFO VMEs as essential fish habitat. Item v. (on indicator species) is ongoing. Suggestion: Amalgamate the review of closures (which was done in 2021) with the formal SAI-VME (which we are doing now). These two related pieces of work are becoming more integrated. The review of closures should probably be one more piece of the overall SAI-VME work. (NB for drafting Comm requests in September). | The work to address this request is ongoing: Part a. Sc is preparing two data layers to address this request: (i) Yearly / Average effort for longlines, groundfish trawls and shrimp trawls for 2010-2021, and (ii). Distribution of catch by fish species (including shrimp) from 2019 onwards. Analysis of these data will be done by WGESA November 2022) and results will presented to SC for consideration in June 2023. Given the current and expected future demand of analyses such as this, SC recommends adoption of a data standards protocol. Part b. is complete, review of the effectiveness of CEM Chapter 2 was provided in the Response June 2022.
| Request #7. The Commission requests that the Scientific Council review the proposed revisions to Annex I.E, Part VI as reflected in COM-SC EAFFM-WP 18-01, for consistency with the taxa list annexed to the VME guide and recommend updates as necessary. | This could stay in 2022 or be rolled into the general request to assess the distribution of VMEs.
Ecosystem State Assessment (WG ESA and EAFFM items) |  | WG EAFFM meeting: July 14-21 2021 | a) SC convened an independent expert panel to review a) FPP and TCIs and b) the adequacy of the analyses for use within the road map. The review panel presented a summary to SC. While the work was endorsed as more than adequate, SC requested additional sensitivity analyses indicated by the reviewers. This work is not expected to delay work planned on the TCI approach for the August WG-EAFFM workshop. b. WG-EAFFM Workshop (August 2022) -WG EAFFM dialogue session took place Oct 2021 to clarify concepts/ideas in preparation for Aug. 2022 workshop. -Plan for the workshop was develped by WG ESA and reviewed by SC and included (1) identifying ecosystem level objectives (2) a proposed red light approach to implmenting TCIs (3) development of tactical rules rules for implementing TCI's was completed. -An agenda for the workshop was drafted by the workshop coordinators (or WG ESA?) and reviewed by SC. Work to support the workshop and progress more generaly on the road map will continue to be carried out by WG ESA
| Request # 5: The Commission requests that Scientific Council continue work on the sustainability of catches aspect of the Ecosystem Roadmap, including: a. In consultation with WG-EAFFM via co-Chairs, convene independent experts to do a scientific review of; a) the estimation of fisheries production potential and total catch indices, and b) the adequacy of this analysis for their proposed use within the NAFO roadmap (Tier 1), while considering how species interactions are expected to be addressed in the future (Tier 2) within the overall Roadmap structure. The outcomes of this review would need to be tabled in June at Scientific Council to be available in advance of the planned workshop in 2022. b. Work to support the WG-EAFFM workshop in 2022, which will explore ecosystem objectives and further develop how the Roadmap may apply to management decision making. c. Continue its work to develop models that support implementation of Tier 2 of the EAFM Roadmap. | WG EAFFM dialogue session Oct 2021 to clarify concepts/ideas in preparation for 2022 workshop.
This request had been completed and a response was finalized at SC in June 2021. The aim of this request was never fully understood so the Commission may follow up in Sept 2021 with a revised request.
| Request # 13. The Commission request that Scientific Council proceed with developing the ecosystem summary sheets for 3M and 3LNO move toward undertaking a joint Workshop with ICES (International Council for the Exploration of the Sea) as part of a peer review of North Atlantic ecosystems. | Time did not allow, given other parallel requests to WG EAFFM and WG ESA. 3LN ecosystem summary sheet was completed in 2020, work will continue on 3M area in remainder of 2021. | Updating ESS': The 3M summary sheet will be worked on in WG ESA meeting in Nov 2022 and reviewed by SC in June 2023. This may need a second phase of work if not completed in November. The 3LNO summary sheet will be updated at the WG ESA meeting in 2022. Work towards undertaking a joint workshop with ICES has been postponed until 2023 (at the earliest) given WG ESA and ICES workload and timetable scheduling contraints this year.
Catch and Bycatch reporting Input to WG-BDS | no requests for this road map component at this time | This has largely been completed in 2021. Two outstanding items in the Action Plan: 4.2. Fishery-specific solutions For NAFO fisheries identified as priorities under Action group 3, assess the merits of specific solutions per fishery, including the development and assessment, with the Scientific Council, of selectivity tests. To be done by :WG-BDS, STACTIC, SC This will likely be done in 2022 as there are currently no plans to have STACTIC and SC work together. 4.3. Identification of best practices Best practices / possible mitigation measures to avoid by-catch per time, area, depth, fleet and fishery. To be Done by: BDS and SC
| Request #11. The Commission requests Scientific Council, jointly with the Secretariat, to conduct ongoing analysis of the Flemish Cap cod fishery data by 2022 in order to: a. monitor the consequences of the management decisions (including the analysis of the redistribution of the fishing effort along the year and its potential effects on ecosystems, the variation of the cod catch composition in lengths/ages, and the bycatch levels of other fish species, benthos in general, and VME taxa in particular), and b. carry out any additional monitoring that would be required, including Div. 3M cod caught as bycatch in other fisheries during the closed period. | Following up on the 2021 the additional actions for 2022 are to carry out a preliminary evaluation to compare/analyse the following before and after the 2021 measures were put in place: • Fishing pattern (e.g. spatial and temporal distribution of catch and effort). • Impact of the fishing activity on VMEs. • Length / age composition of the cod catch. • By-catch levels of 3M cod and distribution in other fisheries. • By-catch levels of other species in the 3M cod fishery. | SC agreed to postpone this analysis until two years of logbook data are available and proposes monitoring the consequences of management decisions every two years. Therefore this request should be included in AM 2013 (to be conducted in 2024)
Monitoring |  | Survey planning, participation in surveys, data collection, dissemination, analysis, interpretation and report writing for SC. Each year for 7 + fisheries surveys as well as a number of oceanographic surveys, and dedicated benthic surveys. CPs plan, conduct surveys, analyse survey data, write, and present survey reports.
| Request #8 The Commission requests Scientific Council to continue to develop a 3-5 year work plan, which reflects requests arising from the 2021 Annual Meeting, other multi-year stock assessments and other scientific inquiries already planned for the near future. The work plan should identify what resources are necessary to successfully address these issues, gaps in current resources to meet those needs and proposed prioritization by the Scientific Council of upcoming work based on those gaps. | A protocol was developed and reviewed by SC for an acoustic survey that will provide abundance and biomass indices. A potential vessel has been identified as well as rough timing window. Remaining work: If European Commission decides to support a new survey, work would include training of personnel for the collection and analysis of acoustic data, including calibration of the acoustic signal. Preparation of the results and their presentation to the SC for use in the alfonsino assessment. Explore possible synergies with US ROV going to the Kükenthal Peak this summer - for now plan is to look at data from the ROV will inform alfonsino survey activities. No survey planned at this time (Aug. 2022) | Timing: Should be updated twice a year, in June and September. Discussion for September update needs at least draft Commission Requests which tend to come the last day of the Commission meeting. To build into the workplanning following the Commission meeting. SC have not recently had opportunity for review of Commission approved requests.

## 2022
Road map component | Request number | Activity | Designated expert | Resources required | Resource gaps | Priority
Stock Assessment |  | Full assessments:
(STACFIS items) |  | June meeting: 3-16 June 2022
| Request #1. The Commission requests that the Scientific Council provide advice for the management of the fish stocks below according to the assessment frequency presented below. * including coastal state requests | GENERAL / COMMON GAPS |  | Both human and financial | More quantitative NAFO SC members for all the assessments at the identified assessment schedule | High (one of the four Commission priorities)
|  |  |  | 2-5 additional SC members with analytical/quantitative expertise | More aging would support SC ability to give comprehensive Science advice (name stocks that are not aged)
|  | 1. 3M cod | Diana Gonzalez Troncoso
|  | 2. 3LNO Thorny skate | Mark Simpson
|  | 3. 3LN redfish (MSE will not complete in time for 2023 TAC) | Ricardo Alpoim | 2 full time agers
|  | 4. 3O redfish | Danny Ings
|  | 5. SA 3+4 Northern shortfin squid | Lisa Hendrickson
Sub area 1:
|  | 7. SA 0 and 1 Greenland halibut | Margaret Trreble
|  | 8. Greenland halibut SA1 inshore | Rysmus Nygaard
NIPAG (targeting September 2021 pre-Commission):
|  | 7. 3M N. shrimp | J. Miquel Casas Sanchez
|  | 8. N. shrimp in Denmark Strait | Frank Riget
|  | 9. N. shrimp SA 0 and 1 | AnnDorte Burmeister
Other stocks without fixed assessm frequency:
| Request # 13 The Commission requests that results from stock assessments and the scientific advice of Cod 2J3KL (Canada), Witch 2J3KL (Canada) and Pelagic Sebastes mentella (ICES Divisions V, XII and XIV; NAFO 1) to be presented to the Scientific Council (SC), and request the SC to prepare a summary of these assessments to be included in its annual report. | Assessments for these domestically assessed stocks have been presented in the last couple years. 2021 was Northern cod only as there was no new assessment for witch flounder or pelagic sebastes mentella. Any new assessment will be presented. | Karen Dwyer (2J3KL cod) Laura Wheland (2J3KL witch flounder) |  |  | Medium
Stock management (HCR's and PA framework) (RBMS items) | Request #4. Scientific Council initiate the first steps in both the 2+3KLMNO Greenland halibut and 3LN redfish MSE processes during 2021-2022, namely: a. Compile catch and survey data and any additional sources of information used in the current models; b. Review and finalize the data inputs for review at the June 2022 Scientific Council meeting when conducting both the 3LN redfish assessment and the assessment of Greenland Halibut Exceptional Circumstances/ Provision of TAC advice c. Time permitting, further work on the respective MSE work plans by the SC-GHL and SC-Redfish subgroups for presentation to WG-RBMS or SC. | Request # 11 3LN redfish MSE: Provisional work plan for a revised MSE for 3LN redfish 1. SC June 2021 – Scoping discussion to provide possible direction for WG-RBMS on a full evaluation of the existing MSE (complete) 2. WG-RBMS Aug 2021 – discussion on scoping exercise and three year calendar for the 3LN redfish MSE. 3. Year 1: data review and development of OM(s) (consensus is required) 4. Year 2: SC review of proposed OMs; obtain consensus on Candidate Management Procedures (CMPs), and with WG-RBMS refine performance statistics 5. Year 3: SC review and testing of CMPs; finalise CMPs to be used in the MSE; and with WG-RBMS evaluate performance statistics and make a final decision on the Management Strategy to propose to the Commission. ***workplan to be reviewed/discussed and finalized by RBMS in August 2021. RBMS will recommend priority stock for MSE. | Ricardo Alpoim and Mark Simpson | Modellers need to be identified. There is funding from Canada for 1 modeller. Not possible for SC to support two parallel MSEs and concurrent PA framework review. Priorirization required. | SC notes that in the next two to three years the revision of two MSs (redfish Div. 3LN and Greenland halibut Sub 2 Div. 3KLMNO) and the PAF revision coincide in time and, given the complexity and the high level of SC resources/capacity required to complete these tasks, SC strongly recommends against trying to perform all three concurrently. Given the review of the PAF is well underway with dedicated external experts participating, the SC recommends that the Commission prioritize one of the MSEs to complete. SC expects the Greenland halibut MSE process to take at least two years to complete and the redfish MSE process to take at least three years. One of these MSE processes will need to be postponed; SC and RBMS will discuss how to proceed to produce management advice for the affected stock in the interim. | High (one of the four Commission priorities)
| Request #2: The Commission requests the SC to monitor the status of Greenland halibut in Subarea 2+Div. 3KLMNO annually to compute the TAC using the agreed HCR and determine whether exceptional circumstances are occurring. If exceptional circumstances are occurring, the exceptional circumstances protocol will provide guidance on what steps should be taken. | Request #2: Greenland Halibut (2+Div 3KLMNO) HCR’s 1) Monitor stock status to compute TAC using HCR 2) Determine how to handle identified exceptional circumstances 3) Provisional workplan for a revised Management Strategy Evaluation for Greenland halibut 1. SC June 2021 - Provisional schedule agreement and discussion of possible direction for WG-RBMS on a general approach in relation to the existing MSE. 2. WG-RBMS Aug 2021 - Schedule finalised and proposed to the Commission. 3. SC Jun 2022 - Proposal and review of the data to be used; consensus required at this time for Operating Model (OM) development to commence. 4. SC Jan 2023 (intersessional) - Proposal and review of OMs to be used; consensus required at this time for Candidate Management Procedure (CMP) testing to commence. 5. WG-RBMS Apr 2023 - Refinement of performance statistics including risk tolerances and constraints; identify initial CMPs. 6. SC Jun 2023 - Review and test CMPs; finalise the suite of CMPs to be used in the Management Strategy Evaluation. 7. WG-RBMS Aug 2023 - Evaluate performance statistics and make a final decision on the Management Strategy to propose to the Commission. 8. COM Sept 2023 - The Commission considers adoption of proposed new Management Strategy for Greenland halibut. | leads: Paul Regular, Brian Healey |  |  | High (one of the four Commission priorities)
| Request #8 : The Commission requests the Scientific Council to continue progression on the review of the NAFO PA Framework in accordance to the PAF review work plan approved in 2020 (NAFO COM-SC Doc. 20-04). | PA framework "Next Steps" (after mapping execise was reviewed by SC in June 2021) -Action 1 – Mapping exercise to be reviewed by RBMS August 2021 -Action 2 - Structural aspects and quantification of uncertainty and risk by September 2022 -Action 3: Workshop with scientists and managers, ~March 2022, to address the ToR 1 and propose of revision of the NAFO PAF to be reviewed by RBMS. -Action 4: The proposed NAFO PAF will be presented to SC and WG-RBMS and the Commission in June, August and September respectively in 2022. -Action 5: Workshop -with scientists and managers after Sept 2022, to develop the guidelines to support the implementation of the proposed NAFO PA framework. Guidelines to be completed by end of 2022. | Karen Dwyer | EU fund is covering cost of external, but there may need to be extra analytical work required at the end, either by externals or SC members. | May have a gap at the end of 2022. | High (one of the four Commission priorities)
Habitat Impact assessment (WG EFFM VME work) |  | WG EAFFM meeting: July 14-21 2021
| Request # 3: The Commission requests that the Scientific Council continue its evaluation of the impact of scientific trawl surveys on VME in closed areas, and the effect of excluding surveys from these areas on stock assessments. | This is almost complete, results from EU surveys to be presented at SC in September. WG-ESA needs to address possible alternative methods to assess changes in VME biomass inside closures to consider potential recoveries. | Diana Gonzalez Troncoso
| Request #6: The Commission requests that SC , in preparation of the re-assessment of NAFO bottom fisheries in 2021 and discussion on VME fishery closures: i. Assess the overlap of NAFO fisheries with VME to evaluate fishery specific impacts in addition to the cumulative impacts for NRA fisheries; ii. Consider clearer objective ranking processes and options for weighting criteria for the overall assessment of significant adverse impacts and the risk of future adverse impacts; iii. Maintain efforts to assess all six FAO criteria including the three FAO functional SAI criteria which could not be evaluated in the current assessment. iv. Provide input and analysis of potential management options, with the goal of supporting meaningful and effective discussions between scientists and managers at the 2021 WG-EAFFM meeting; (includes a revision to seamount closure boundaries proposed in 2020) v. Continue to work on the VME indicator species as listed in Annex IE, Section VI to prepare for the next assessment. | The re-assessment will be complete as of June 2021 but there will be work required to prepare for the next re-assessment. More work is required for point iii on SAI criteria, including standardizing benthic biomass data across surveys and evaluating the significance of NAFO VMEs as essential fish habitat. Item v. (on indicator species) is ongoing. Suggestion: Amalgamate the review of closures (which was done in 2021) with the formal SAI-VME (which we are doing now). These two related pieces of work are becoming more integrated. The review of closures should probably be one more piece of the overall SAI-VME work. (NB for drafting Comm requests in September). | Ellen Kenchington Andy Kenny | Work overload issue trying to do it all in one go (review of closures and SAI-VME work). At the moment the work is staggered between years on account of doing separate assessments. SC could manage this by establishing a timetable which effectively maintains the staggered approach but presents a single integrated assessment every 5 years.
| Request #7. The Commission requests that the Scientific Council review the proposed revisions to Annex I.E, Part VI as reflected in COM-SC EAFFM-WP 18-01, for consistency with the taxa list annexed to the VME guide and recommend updates as necessary. | This could stay in 2022 or be rolled into the general request to assess the distribution of VMEs. | Ellen Kenchington Andy Kenny
Ecosystem State Assessment (WG ESA and EAFFM items) | Request # 5: The Commission requests that SC continue to refine work on the Ecosystem Road Map: The Commission requests that SC continue to refine work on the Ecosystem Road Map: • Continue to test the reliability of the ecosystem production potential model and other related models • Report on these results to WG-EAFFM and WG-RBMS to further develop how it may apply to management decisions • Develop options of how ecosystem advice could inform management decisions, an issue which is directly linked to the results of the foreseen EAFM roadmap workshop. • Continue its work to develop models that support implementation of Tier 2 of the EAFM Roadmap." | WG EAFFM dialogue session Oct 2021 to clarify concepts/ideas in preparation for 2022 workshop. WG-EAFFM Workshop (deferred to 2022) • Identify ecosystem level objectives • Identify elements of the potential application of an ecosystems approach to fisheries management including principles of application • Explore the existing body of practice (successes and failures) of implementing an ecosystem approach • Identify the types of ecosystem-based fisheries information that may inform the future development of the NAFO PA. Work to support these sessions and progress more generaly on the road map will be carried out by WG ESA | Mariano Koen-Alonso Pierre Pepin |  |  | High
| Request #17: The Commission requests the Scientific Council to provide information to the Commission at its next annual meeting on sea turtles, sea birds, and marine mammals that are present in NAFO Regulatory Area based on available data. | This request had been completed and a response was finalized at SC in June 2021. The aim of this request was never fully understood so the Commission may follow up in Sept 2021 with a revised request. | Pablo Durán Muñoz Mar Sacau Garry Stenson Nick Duprey
| Request # 18. The Commission requests that the Scientific Council proceed with developing the ecosystem summary sheets for 3M and 3LNO move toward undertaking a joint Workshop with ICES (International Council for the Exploration of the Sea) as part of a peer review of North Atlantic ecosystems. | Time did not allow, given other parallel requests to WG EAFFM and WG ESA. 3LN ecosystem summary sheet was completed in 2020, work will continue on 3M area in remainder of 2021. | Pierre Pepin |  |  | Medium/High
Catch and Bycatch reporting Input to WG-BDS | Request #4. The Commission requests the Scientific Council to implement the steps of the Action plan relevant to the Scientific Council and in particular the tasks identified under section 2.2 of the Action Plan, for progression in the management and minimization of Bycatch and discards (COM Doc. 17-26). • Tasks outlined in Tasks 3.1 and 3.2 of the NAFO Action Plan in the Management and Minimization of Bycatch and Discards (COM Doc. 17-26). | This has largely been completed in 2021. Two outstanding items in the Action Plan: 4.2. Fishery-specific solutions For NAFO fisheries identified as priorities under Action group 3, assess the merits of specific solutions per fishery, including the development and assessment, with the Scientific Council, of selectivity tests. To be done by :WG-BDS, STACTIC, SC This will likely be done in 2022 as there are currently no plans to have STACTIC and SC work together. 4.3. Identification of best practices Best practices / possible mitigation measures to avoid by-catch per time, area, depth, fleet and fishery. To be Done by: BDS and SC
| Request #9. The Commission requests that the Scientific Council Work with WG- BDS to identify areas and times where bycatch and discards of Greenland sharks have a higher rate of occurrence in time for consideration by the Commission in 2021 to inform the development of measures to reduce bycatch in the NRA. | Complete pending concurrence of Commission in September 2022
| Request #14: The Commission requests the Scientific Council, jointly with the Secretariat, to conduct ongoing analysis of the Flemish Cap cod fishery data by 2022 in order to: (1) monitor the consequences of the management decisions (including the analysis of the redistribution of the fishing effort along the year and its potential effects on ecosystems, the variation of the cod catch composition in lengths/ages, and the bycatch levels of other fish species, benthos in general, and VME taxa in particular), and (2) carry out any additional monitoring that would be required, including Div. 3M cod caught as bycatch in other fisheries during the closed period. | Following up on the 2021 the additional actions for 2022 are to carry out a preliminary evaluation to compare/analyse the following before and after the 2021 measures were put in place: • Fishing pattern (e.g. spatial and temporal distribution of catch and effort). • Impact of the fishing activity on VMEs. • Length / age composition of the cod catch. • By-catch levels of 3M cod and distribution in other fisheries. • By-catch levels of other species in the 3M cod fishery. | Diana Gonzalez Troncoso | Haul by haul data will be provided by the Secretariat and samples (catch and length distributions) from the CPs . Likely there will be data gaps because of lack of samples related to COVID 19 which could compromise the analyses.
Monitoring |  | Survey planning, participation in surveys, data collection, dissemination, analysis, interpretation and report writing for SC. Each year for 7 + fisheries surveys as well as a number of oceanographic surveys, and dedicated benthic surveys. CPs plan, conduct surveys, analyse survey data, write, and present survey reports. | Rick Rideout, Ricardo Alpoim, Fernando González and Diana Gonzalez Troncoso
| Sept. 2020 Request # 12. The Commission requests the Scientific Council review submitted protocols for a survey methodology to inform the assessment of Splendid Alfonsino. The Scientific Council to report on the outcome of this work at next Commission annual meeting. | A protocol was developed and reviewed by SC for an acoustic survey that will provide abundance and biomass indices. A potential vessel has been identified as well as rough timing window. Remaining work: If European Commission decides to support a new survey, work would include training of personnel for the collection and analysis of acoustic data, including calibration of the acoustic signal. Preparation of the results and their presentation to the SC for use in the alfonsino assessment. Explore possible synergies with US ROV going to the Kükenthal Peak this summer - for now plan is to look at data from the ROV will inform alfonsino survey activities. Earliest survey date would be summer 2022. |  |  | Data analysis, were the survey to be carried out, would include 1 month of work from IEO.

## 2021
Road map component | Activity | Designated expert | Resources required | Resource gaps | Priority
Stock Assessment | Full assessments:
(STACFIS items) | June meeting: May 27-June 11 2021
| GENERAL / COMMON GAPS |  | Both human and financial | More quantitative NAFO SC members for all the assessments at the identified assessment schedule | Medium-High
|  |  | 2-5 additional SC members with analytical/quantitative expertise | More aging would support SC ability to give comprehensive Science advice (eg 3NO witch flounder and 3LNO yellowtail are not aged) | Medium-High
| 1. 3M cod | Diana Gonzalez Troncoso
| 2. 3M redfish | Ricardo Alpoim | 2 full time agers | To better understand redfish stock dynamics within and among areas, redfish should be speciated in the surveys | Medium
| 3. 3NO capelin | Konstantin Fomin
| 4. 3NO cod | Rick Rideout
| 5. 3LNO yellowtail | Dawn Maddock Parsons | 2 full time agers
| 6. 3LNO American plaice | Laura Wheeland
| 7. 3NO White hake | Mark Simpson
Sub area 1:
Only shrimp listed under NIPAG
NIPAG (targeting September 2021 pre-Commission):
| 7. 3M N. shrimp | J. Miquel Casas Sanchez
| 8. N. shrimp in Denmark Strait | Frank Riget
| 9. N. shrimp SA 0 and 1 | AnnDorte Burmeister |  | A paired trawl survey will be required for calibration between the charter and new vessel for the SA 0 and 1 survey (shrimp and Greenland Halibut) | High
10. 3LNO Northen shrimp
Other stocks without fixed assessm frequency:
| Splendid Alfonsino - survey review | Pablo Carrera |  | S. alfonsino has no survey. Some fisheries independent information or carefully monitored experimental fishery would be required to monitor the stock provide Science advice. | Low-Medium
***note IMR for squid will be targetted for the Annual meeting
Stock management (HCR's and PA framework) (RBMS items) | 1) 3LN redfish: review of discussion paper on conservation plan and harvest control rules 2) September 2020 SC: scoping for a full review/evaluation of the management strategy (implementation period ends in 2021, SC provided advice for 2021-22) ( Commission requests SC provide guidance on the process of conducting of a full review/evaluation of the management strategy in time for September 2022 Commission meeting) |  | SC to identify a designated expert |  | High
| Greenland Halibut (2+Div 3KLMNO) HCR’s 1) Monitor stock status to compute TAC using HCR 2) Determine whether there are exceptional circumstances 3) Develop workplan to update Greenland Halibut MSE by Sept 2022 for 2023 decision | leads: Paul Regular, Brian Healey |  |  | High
| PA framework Progress on the review of the NAFO PA Framework. 1) Workplan items for 2021: Review of structual technical items • Review of and proposal for ToRs related to mapping objectives: ToRs 1a,c and g. Deadline SC June 2021 • Present results to WG-RBMS after June 2021 SC • Review of and proposal for ToRs related to structural aspects and quantification of uncertainty and risk. Deadline for results to SC: ToRs 1b, d, e and f. Deadline for results November 2021 2) Engagement with management 3) develop funding proposal to EU (complete?) 4) Finalize jurisdictional review 5) Identify 3 external experts (and develop ToRs to do so) | Technical team: Karen Dwyer, Julie Marentette |  | EU fund for 2020 available | Top priority
Habitat Impact assessment (WG EFFM VME work) | WG EAFFM meeting: July 16-18 2019 · Evaluation of the impact of scientific trawl surveys on VME in closed areas · Evaluate the effect of excluding surveys from closed areas on stock assessments.
In preparation of the next re-assessment of NAFO bottom fisheries in 2021: · Assess the overlap of NAFO fisheries with VME to evaluate fishery specific impacts in addition to the cumulative impacts; · Continue to work on non-sponge and coral VMEs (for example bryozoan and sea squirts) to prepare for the next assessment. · Maintain efforts to assess all of the six FAO criteria including the three FAO functional SAI criteria which could not be evaluated in the current assessment. · Consider clearer objective ranking processes and options for objective weighting criteria for the overall assessment of significant adverse impacts and the risk of future adverse impacts;
Seamounts · Provide map and coordinates of Kükenthal Peak (related to S. alphonsino)
Impact of oil and gas · Monitor and provide updates on research related to the potential impact of activities other than fishing in the Convention Area.
Ecosystem State Assessment (WG ESA and EAFFM items) | Road map Tier 1 · Continue to refine work on the Ecosystem Road Map, including testing the reliability of the ecosystem production potential model and other related models · Report on these results to WG –EAFFM and WG- RBMS to further develop how it may apply to management decisions.
Catch and Bycatch reporting Input to WG-BDS | Action Plan · Implement SC-related steps of the Action plan (in particular the tasks for progression in the management and minimization of Bycatch and discards)
WG- Bycatch, Discards, and Selectivity · Work with WG- BDS to identify areas and times where bycatch and discards of Greenland sharks have a higher rate of occurrence in time for consideration by the Commission in 2021
CESAG | SC members participate in review of implementation of CESAG enhanced method and results.
Monitoring SC generally and relates to STACFIS and STACFEN work | Survey planning, participation in surveys, data collection, dissemination, analysis, interpretation and report writing for SC. Each year for 7 + fisheries surveys as well as a number of oceanographic surveys, and dedicated benthic surveys. Survey sub-group Symposium

## 2020
Road map component | Activity | Designated expert | Resources required | Resource gaps | Priority
Stock Assessment (STACFIS items) | Full assessments: June meeting: May 28-June 12 2020 1. 3M cod 2. 3M American Plaice 3. 3NO Capelin 4. Greenland Halibut SA2 +3KLMNO 5. 3LNO Thorny skate 6. 3NO Witch flounder (SC of its own accord) 6.Greenland Halibut SA 0 and 1 Sub area 1: 7. 8. Demersal deep-sea Redfish, 9.Atlantic Wolffish 10. Spotted Wolffish 11. Greenland Halibut SA 1 inshore NIPAG: (Targetting September pre-Commission) 12. 3LN N. shrimp 13. 3M N. shrimp 14. N. Shrimp in Denmark Strait 15. N. shrimp SA 0 and 1 ***note IMR for squid will be targetted for the Annual meeting | Full assessments: June meeting: May 28-June 12 2020 1. Diana Gonzalez Troncoso 2. Laura Wheland 3. Ivan Tretiakov 4. Joanne Morgan 5. Mark Simpson 6. Dawn Maddock Parsons 7. 8. 9. 10. 11. NIPAG: 12. Katherine Skanes 13. J. Miquel Casas Sanchez 14. Frank Riget 15. AnnDorte Burmeister | Both human and financial 2-5 additional SC members with analytical/quantitative expertise 2 full time agers for 3NO witch flounder, 3LNO yellowtail, redfish, S. alfonsino allocated time to plan a survey. May not take place for a number of years, but planning before would be required. | For some assessments limited Science advice can be provided. Advice could be improved with the following: More quantitative NAFO SC members for all the assessments at the identified assessment schedule More aging would support SC ability to give comprehensive Science advice (name stocks that are not aged) S. alfonsino has no survey. Some fisheries independent information or carefully monitored experimental fishery would be required to monitor the stock provide Science advice. To better understand redfish stock dynamics within and among areas, redfish should be speciated in the surveys. A paired trawl survey will be required for calibration between the charter and new vessel for the SA 0 and 1 survey (shrimp and Greenland Halibut) | High Medium-High Medium-High Low to Medium for now until requested Medium High
Stock management (HCR's and PA framework) (RBMS items) | 3LN redfish HCR· · Calculation for 2020 · reviewing/evaluating HCR's (SC advice due for 2021 decision).
Greenland Halibut (2+Div 3KLMNO) HCR’s · Monitor stock status to compute TAC using HCR · Determine whether there are exceptional circumstances
| 3M cod MSE: Meeting RBMS Sept 21 2019 · Implement agreed steps to have MSE ready for September 2019 for harvest decision for the 2020 season | Technical team: Diana Gonzalez Trancoso; Fernando Gonzalez, Agurtzane Urtizberea, Jose de Oliveira, Tomas Brunnel, Panayiota Apostakali, Ricardo Alpoim, Antonio Avila de Melo and Carmen Fernandez | Technical developments and preparatory work: 250.000€ (EU Financial support) | Inadequate financial resources beyond December 2019 | Top priority
SC meeting January 2019 RBMS meeting April 2019
| PA framework · Progress on the review of the NAFO PA Framework. |  |  | EU fund for 2020 available | Top priority
Habitat Impact assessment (WG EFFM VME work) | WG EAFFM meeting: July 16-18 2019 · Evaluation of the impact of scientific trawl surveys on VME in closed areas · Evaluate the effect of excluding surveys from closed areas on stock assessments.
In preparation of the next re-assessment of NAFO bottom fisheries in 2021: · Assess the overlap of NAFO fisheries with VME to evaluate fishery specific impacts in addition to the cumulative impacts; · Continue to work on non-sponge and coral VMEs (for example bryozoan and sea squirts) to prepare for the next assessment. · Maintain efforts to assess all of the six FAO criteria including the three FAO functional SAI criteria which could not be evaluated in the current assessment. · Consider clearer objective ranking processes and options for objective weighting criteria for the overall assessment of significant adverse impacts and the risk of future adverse impacts;
Seamounts · Provide map and coordinates of Kükenthal Peak (related to S. alphonsino)
Impact of oil and gas · Monitor and provide updates on research related to the potential impact of activities other than fishing in the Convention Area.
Ecosystem State Assessment (WG ESA and EAFFM items) | Road map Tier 1 · Continue to refine work on the Ecosystem Road Map, including testing the reliability of the ecosystem production potential model and other related models · Report on these results to WG –EAFFM and WG- RBMS to further develop how it may apply to management decisions.
Catch and Bycatch reporting Input to WG-BDS | Action Plan · Implement SC-related steps of the Action plan (in particular the tasks for progression in the management and minimization of Bycatch and discards)
WG- Bycatch, Discards, and Selectivity · Work with WG- BDS to identify areas and times where bycatch and discards of Greenland sharks have a higher rate of occurrence in time for consideration by the Commission in 2021
CESAG | SC members participate in review of implementation of CESAG enhanced method and results.

## 2019
Road map component | Activity | Designated expert | Resources required | Resource gaps | Priority
Stock Assessment (STACFIS items) | Full assessments: June meeting: May 31-June 13 2019 1. 3M Cod 2. 3M Redfish-ext. review 3. 3O Redfish 4. Grenadier 5. N. Shortfin squid 6. S. alphonsino 7. 3NO Witch-ext. review 8. 3M Golden redfish (including request #7 on implications of species splitting) 9. White hake NIPAG: 1) 3M shrimp | Full assessments: June meeting: May 31-June 13 2019 1. Diana Gonzalez Troncoso 2. Antonio Avila de Melo 3. Danny Ings 4. Fernando Gonzalez-Costas 5. Lisa Hendrickson 6. Fernando Gonzalez-Costas 7. Joanne Morgan 8. Ricardo Alpoim 9. Mark Simpson NIPAG: 1) J. Miquel Casas Sanchez | Both human and financial 2-5 additional members with analytical/quantitative expertise 2 full time agers for witch flounder, yellowtail, redfish, S. alfonsino Dedicated time to plan a survey or work with industy to design an experimental fishery. May not take place for a number of years, but planning before would be required. | For some assessments limited Science advice can be provided. Advice could be improved with the following: More quantitative NAFO SC members are to all the assessments at the identified assessment schedule More aging would support SC ability to give comprehensive Science advice (name stocks that are not aged) S. alfonsino has no survey. Some fisheries independent information or carefully monitored experimental fishery would be required to monitor the stock provide Science advice. To better understand redfish stock dynamics within and among areas, redfish should be speciated in the surveys. A paired trawl survey will be required for calibration between the charter and new vessel for the SA 0 and 1 survey (shrimp and Greenland Halibut) | Medium-High Medium-High Medium for now, High to re-open fishery Medium High
Stock management (HCR's and PA framework) (RBMS items) | 3LN redfish HCR· · Calculation for 2020 · Consider timing for reviewing/evaluating HCR's (SC advice due for 2021 decision).
Greenland Halibut (2+Div 3KLMNO) HCR’s · Monitor stock status to compute TAC using HCR · Determine whether there are exceptional circumstances
| 3M cod MSE: Meeting RBMS Sept 21 2019 · Implement agreed steps to have MSE ready for September 2019 for harvest decision for the 2020 season | Technical team: Diana Gonzalez Trancoso; Fernando Gonzalez, Agurtzane Urtizberea, Jose de Oliveira, Tomas Brunnel, Panayiota Apostakali, Ricardo Alpoim, Antonio Avila de Melo and Carmen Fernandez | Technical developments and preparatory work: 250.000€ (EU Financial support) | Inadequate financial resources beyond December 2019 | Top priority
SC meeting January 2019 RBMS meeting April 2019
| PA framework · Progress on the review of the NAFO PA Framework. |  |  | EU fund for 2020 available | Top priority
Habitat Impact assessment (WG EFFM VME work) | WG EAFFM meeting: July 16-18 2019 · Evaluation of the impact of scientific trawl surveys on VME in closed areas · Evaluate the effect of excluding surveys from closed areas on stock assessments.
In preparation of the next re-assessment of NAFO bottom fisheries in 2021: · Assess the overlap of NAFO fisheries with VME to evaluate fishery specific impacts in addition to the cumulative impacts; · Continue to work on non-sponge and coral VMEs (for example bryozoan and sea squirts) to prepare for the next assessment. · Maintain efforts to assess all of the six FAO criteria including the three FAO functional SAI criteria which could not be evaluated in the current assessment. · Consider clearer objective ranking processes and options for objective weighting criteria for the overall assessment of significant adverse impacts and the risk of future adverse impacts;
Seamounts · Provide map and coordinates of Kükenthal Peak (related to S. alphonsino)
Impact of oil and gas · Monitor and provide updates on research related to the potential impact of activities other than fishing in the Convention Area.
Ecosystem State Assessment (WG ESA and EAFFM items) | Road map Tier 1 · Continue to refine work on the Ecosystem Road Map, including testing the reliability of the ecosystem production potential model and other related models · Report on these results to WG –EAFFM and WG- RBMS to further develop how it may apply to management decisions.
Catch and Bycatch reporting Input to CESAG WG-BDS | Action Plan · Implement SC-related steps of the Action plan (in particular the tasks for progression in the management and minimization of Bycatch and discards)
WG- Bycatch, Discards, and Selectivity · Work with WG- BDS to identify areas and times where bycatch and discards of Greenland sharks have a higher rate of occurrence in time for consideration by the Commission in 2021
Monitoring SC generally and relates to STACFIS and STACFEN work | Survey planning, participation in surveys, data collection, dissemination, analysis, interpretation and report writing for SC. Each year for 7 + fisheries surveys as well as a number of oceanographic surveys, and dedicated benthic surveys.

## 2022-2023
Road map component | Request number | Activity | Designated expert | Resources required | Resource gaps | Priority
This 2022-2023 Tab covers work planned for mid-June 2022 to mid-June 2023
Stock Assessment |  | Full assessments:
June meeting: ~2-15 June 2023
| Request #1. The Commission requests that the Scientific Council provide advice for the management of the fish stocks below according to the assessment frequency presented below. * including coastal state requests |  |  | Both human and financial | More quantitative NAFO SC members for all the assessments at the identified assessment schedule | High (one of the four Commission priorities)
|  |  |  | 2-5 additional SC members with analytical/quantitative expertise | More aging would support SC ability to give comprehensive Science advice (name stocks that are not aged)
|  | 1. 3M Cod | Diana Gonzalez Troncoso
|  | 2. 3M Redfish | Ricardo Alpoim
|  | 3. 3NO White hake | Katherine Sosebee
|  | 4. 3M American plaice | Ricardo Alpoim
|  | 5. 3LNO Yelowtail flounder | Dawn Maddock Parsons
|  | 6. 3M Golden redfish | Ricardo Alpoim
Sub area 1: to be checked
|  | 7. Demersal deep-sea redfish | Rasmus Nygaard
|  | 8. Atlantic wolfish | Rasmus Nygaard
|  | 9. Spoted wolfish | Rasmus Nygaard
NIPAG (targeting September 2023 pre-Commission):
|  | 10. 3M Northern shrimp | J. Miquel Casas Sanchez
|  | 11. 3LNO Northern shrimp | Katherine Skanes
|  | 12. Northern shrimp in Denmark Strait | Tanja B. Buch
|  | 13. Northern shrimp in SA 0 and 1 | AnnDorte Burmeister
Other stocks without fixed assessment frequency:
| Request # 10 The Commission requests that any new results from stock assessments and the scientific advice of Cod 2J3KL (Canada), Witch 2J3KL (Canada) and Pelagic Sebastes mentella (ICES Divisions V, XII and XIV; NAFO 1) to be presented to the Scientific Council and request the Scientific Council to prepare a summary of these assessments to be included in its annual report. | Assessments for these domestically assessed stocks have been presented in the last couple years. In 2022 there was no Northern cod assessment as a key survey had been cancelled. The latest assessment for witch flounder was presented. The stock shows some improvement but remains below the Canadian Blim. The 2021 ICES assessment for Pelagic sebastes mentella was presented and the results showed that both the shallow and deep stocks are well below Blim. | Karen Dwyer, Laura Wheeland, Ricardo Alpoim |  |  | Medium
| Request #9: The Commission requests that Scientific Council do a full assessment for Div. 3LN redfish and provide advice based on the projection for various harvest levels for two-years (2023 and 2024) to evaluate the impacts according to the performance statistics from NAFO CEM Annex I.H. | The updated ASPIC model was not accepted by STACFIS because the r-value was deemed implausibly high for a long-lived species like redfish.The stock is currently unknown as the ASPIC model was rejected. The mean of the standardized survey timeseries indicates aggregate biomass is at the long-term mean. An interim limit reference point was adopted as this stock will be undergoing an MSE.
Stock management (HCR's and PA framework) (RBMS items) | Request #4. Scientific Council initiate the first steps in both the 2+3KLMNO Greenland halibut and 3LN redfish MSE processes during 2021-2022, namely: a. Compile catch and survey data and any additional sources of information used in the current models; b. Review and finalize the data inputs for review at the June 2022 Scientific Council meeting when conducting both the 3LN redfish assessment and the assessment of Greenland Halibut Exceptional Circumstances/ Provision of TAC advice c. Time permitting, further work on the respective MSE work plans by the SC-GHL and SC-Redfish subgroups for presentation to WG-RBMS or SC. | Request # 4 3LN redfish MSE: Provisional work plan for a revised MSE for 3LN redfish 1. SC June 2021 – Scoping discussion to provide possible direction for WG-RBMS on a full evaluation of the existing MSE (complete) 2. WG-RBMS Aug 2021 – discussion on scoping exercise and three year calendar for the 3LN redfish MSE. 3. Year 1: data review (SC June 2022) to be reviewed at WG-RBMS in August 2022? or complete 4. Year 2: SC review of proposed OMs; obtain consensus on Candidate Management Procedures (CMPs), and with WG-RBMS refine performance statistics 5. Year 3: SC review and testing of CMPs; finalise CMPs to be used in the MSE; and with WG-RBMS evaluate performance statistics and make a final decision on the Management Strategy to propose to the Commission. Request #4: Greenland Halibut (2+Div 3KLMNO) HCR’s 1) Monitor stock status to compute TAC using HCR 2) Determine how to handle identified exceptional circumstances 3) Provisional workplan for a revised Management Strategy Evaluation for Greenland halibut 1. SC June 2021 - Provisional schedule agreement and discussion of possible direction for WG-RBMS on a general approach in relation to the existing MSE. 2. WG-RBMS Aug 2021 - Schedule finalised and proposed to the Commission. 3. SC Jun 2022 - Proposal and review of the data to be used (Complete) 4. SC Jan 2023 (intersessional) - Proposal and review of OMs to be used; consensus required at this time for Candidate Management Procedure (CMP) testing to commence. 5. WG-RBMS Apr 2023 - Refinement of performance statistics including risk tolerances and constraints; identify initial CMPs. 6. SC Jun 2023 - Review and test CMPs; finalise the suite of CMPs to be used in the Management Strategy Evaluation. 7. WG-RBMS Aug 2023 - Evaluate performance statistics and make a final decision on the Management Strategy to propose to the Commission. 8. COM Sept 2023 - The Commission considers adoption of proposed new Management Strategy for Greenland halibut. | Bob Rogers, Paul Regular and Mark Simpson | Modellers need to be identified. There is funding from Canada for 1 modeller. Not possible for SC to support two parallel MSEs and concurrent PA framework review. Priorirization required. | SC notes that in the next two to three years the revision of two MSs (redfish Div. 3LN and Greenland halibut Sub 2 Div. 3KLMNO) and the PAF revision coincide in time and, given the complexity and the high level of SC resources/capacity required to complete these tasks, SC strongly recommends against trying to perform all three concurrently. Given the review of the PAF is well underway with dedicated external experts participating, the SC recommends that the Commission prioritize one of the MSEs to complete. SC expects the Greenland halibut MSE process to take at least two years to complete and the redfish MSE process to take at least three years. One of these MSE processes will need to be postponed; SC and RBMS will discuss how to proceed to produce management advice for the affected stock in the interim. | High (one of the four Commission priorities)
| Request #2: The Commission requests the Scientific Council to monitor the status of Greenland halibut. Conditional on the absence of other reasons for Exceptional Circumstances arising (other than the missing Canadian spring 3LNO survey), to calculate in 2022 the HCR adjusting the TAC advised for 2022 using four survey indices (Canadian fall 2J3K, Canadian fall 3LNO, EU 3M 0-1400m, and EU-Spain 3NO surveys) to provide TAC advice for 2023. If other reasons for exceptional circumstances are occurring, the EC protocol will provide guidance on what steps should be taken. | Request #2: Greenland Halibut (2+Div 3KLMNO) HCR’s Request #2: Greenland Halibut (2+Div 3KLMNO) HCR’s 1) Monitor stock status to compute TAC using HCR (complete) 2) Determine how to handle identified exceptional circumstances (complete) Exceptional circumstances were triggered because of missing surveys and analyses were carried out to see if TAC could still be calculated with the available information. The conclusion was yes (the tAC was not very sensitive to leaving out spring 3LNO so the TAC for 2023 was calculated) | leads: Paul Regular, Brian Healey |  |  | High (one of the four Commission priorities)
| Request #7 : The Commission requests Scientific Council to continue progression on the review of the NAFO PA Framework in accordance to the PAF review work plan approved in 2020 (NAFO COM-SC Doc. 20-04). | Completed: mapping exercise, jurisdictional review, and review on uncertainty and risk, Aug 2022 workshop draft agenda PA framework "Next Steps" Draft agenda to be reviewed by RBMS and sent as provisional to Commission. PAWG July workshop to develop alternative proposals, SC review in late July before RBMS in August. -"Action 3": Workshop with scientists and managers, August 2022, to address the ToR 1 and consider one or two alternative proposals to the current NAFO PA from PAWG. Second workshop to explore tools for testing PA framework(s?) -Action 4: The proposed NAFO PAF will be presented to SC and WG-RBMS and the Commission in date TBD -Action 5: Workshop -with scientists and managers after [date TBD], to develop the guidelines to support the implementation of the proposed NAFO PA framework. Guidelines to be completed by [date TBD]. -One month before the end of the EU grant (end is December 2022 so November 2022) we need to send a letter with a justification for a new date to extend the time frame for work. | Fernando Gonzalez-Costas | EU fund is covering cost of external, but there may need to be extra analytical work required at the end, either by externals or SC members. | Will seek funding extension for the end of 2022. | High (one of the four Commission priorities)
Habitat Impact assessment (WG EFFM VME work) +A33 | Request # 3: The Commission requests that the Scientific Council continue its evaluation of the impact of scientific trawl surveys on VME in closed areas, and the effect of excluding surveys from these areas on stock assessments. | This is almost complete, results from EU surveys to be presented at SC in September. WG-ESA needs to address possible alternative methods to assess changes in VME biomass inside closures to consider potential recoveries. | Diana Gonzalez Troncoso
| Request #6 The Commission requests that Scientific Council, in relation to VME analyses: a. Conduct a re-assessment of its previously recommended closures of 7a, 11a, 14a and 14b, incorporating catch and effort data for fisheries of shrimp from 2020 and 2021 into the fishing impact assessments. This work is to be completed by the 2023 Scientific Council meeting. b. Review the effectiveness of NAFO CEM, Chapter 2 from a scientific and technical perspective and report back to the WG-EAFFM. WG-EAFFM would subsequently in 2022 consider whether any modifications to this Chapter should be recommended. | The work to address this request is ongoing: Part a. Sc is preparing two data layers to address this request: (i) Yearly / Average effort for longlines, groundfish trawls and shrimp trawls for 2010-2021, and (ii). Distribution of catch by fish species (including shrimp) from 2019 onwards. Analysis of these data will be done by WGESA November 2022) and results will presented to SC for consideration in June 2023. Given the current and expected future demand of analyses such as this, SC recommends adoption of a data standards protocol. Part b. is complete, review of the effectiveness of CEM Chapter 2 was provided in the Response June 2022. | Ellen Kenchington Andy Kenny Mariano Koen-Alonso | As part of developing a data standards protocol there is likely to be a requirement for additional secretariat resources to support the need for on-going management and maintenance of a GIS database for VME and bottom fisheries re-assessments. From last year: Work overload issue trying to do it all in one go (review of closures and SAI-VME work). At the moment the work is staggered between years on account of doing separate assessments. SC could manage this by establishing a timetable which effectively maintains the staggered approach but presents a single integrated assessment every 5 years.
| Request #12 The Commission requests Secretariat and the Scientific Council with other international organizations, such as the FAO and ICES to inform the Scientific Council’s work related to the potential impact of activities other than fishing in the Convention Area. This would be conditional on CPs providing appropriate additional expertise to Scientific Council. | The SC will monitor the spatial overlap with NAFO bottom fisheries, NAFO closures and VMEs poligons of the activities other than fiishing and especially oil and gas activities that heve increased in recent years. SC requests access to the data and analysis from monitoring programs of oil and gas activities from Contracting Parties. | Mar Sacau, Pablo Duran |  | SC notes that current expertise within SC WGESA in particular, and SC in general, is insufficient to allow SC to fully assess the long term impacts of these activities on fisheries resources, VMEs and the wider marine ecosystem. SC request CPs to provide relevant additional expertise monitoring and evaluation of marine environmental impacts of activities other than fishing (e.g. oil and gas).
Ecosystem State Assessment (WG ESA and EAFFM items) | Request # 13. The Commission request that Scientific Council proceed with developing the ecosystem summary sheets for 3M and 3LNO move toward undertaking a joint Workshop with ICES (International Council for the Exploration of the Sea) as part of a peer review of North Atlantic ecosystems. | Updating ESS': The 3M summary sheet will be worked on in WG ESA meeting in Nov 2022 and reviewed by SC in June 2023. This may need a second phase of work if not completed in November. The 3LNO summary sheet will be updated at the WG ESA meeting in 2022. Work towards undertaking a joint workshop with ICES has been postponed until 2023 (at the earliest) given WG ESA and ICES workload and timetable scheduling contraints this year. | vacant | Need two dedicated experts to WG ESA to work on the analyses and compilation of the necessary data and information for the two EPUs. The previous DE responsible for 3LNO is no longer in NAFO SC. The reduction in WGESA capacity in 2021 has had direct impacts on this work, resulting in limited progress to date on the work required for this request. SC created two positions in June 2022 to coordinate the ESS work (EDE - ecosystem designated expert). These positions needs to be filled. |  | High
| Request # 5: The Commission requests that Scientific Council continue work on the sustainability of catches aspect of the Ecosystem Roadmap, including: a. In consultation with WG-EAFFM via co-Chairs, convene independent experts to do a scientific review of; a) the estimation of fisheries production potential and total catch indices, and b) the adequacy of this analysis for their proposed use within the NAFO roadmap (Tier 1), while considering how species interactions are expected to be addressed in the future (Tier 2) within the overall Roadmap structure. The outcomes of this review would need to be tabled in June at Scientific Council to be available in advance of the planned workshop in 2022. b. Work to support the WG-EAFFM workshop in 2022, which will explore ecosystem objectives and further develop how the Roadmap may apply to management decision making. c. Continue its work to develop models that support implementation of Tier 2 of the EAFM Roadmap. | a. Estimation of FPP and TCI a) SC convened a three person independent expert panel to review a) FPP and TCIs and b) the adequacy of the analyses for use within the road map. The review panel presented a consolidated summary to SC. While the work was endorsed as more than adequate, SC requested additional sensitivity analyses indicated by the reviewers. This work is not expected to delay work planned on the TCI approach for the August WG-EAFFM workshop. b. WG-EAFFM Workshop (August 2022) -WG EAFFM dialogue session took place Oct 2021 to clarify concepts/ideas in preparation for Aug. 2022 workshop. -Plan for the workshop was develped by WG ESA and reviewed by SC and included (1) identifying ecosystem level objectives (2) a proposed red light approach to implmenting TCIs (3) development of tactical rules rules for implementing TCI's was completed. -An agenda for the workshop was drafted by the workshop coordinators (or WG ESA?) and reviewed by SC. Work to support the workshop and progress more generaly on the road map will continue to be carried out by WG ESA | Mariano Koen-Alonso | Reflect discussion re including academics, secreteriat support Support for Tier 2 development, | At present, there are no people available in SC to engage fully on Tier 2 development, | High
Road map Tier Two (multi-species) | Request # 5: The Commission requests that Scientific Council continue work on the sustainability of catches aspect of the Ecosystem Roadmap, including: a. In consultation with WG-EAFFM via co-Chairs, convene independent experts to do a scientific review of; a) the estimation of fisheries production potential and total catch indices, and b) the adequacy of this analysis for their proposed use within the NAFO roadmap (Tier 1), while considering how species interactions are expected to be addressed in the future (Tier 2) within the overall Roadmap structure. The outcomes of this review would need to+B38 be tabled in June at Scientific Council to be available in advance of the planned workshop in 2022. b. Work to support the WG-EAFFM workshop in 2022, which will explore ecosystem objectives and further develop how the Roadmap may apply to management decision making. c. Continue its work to develop models that support implementation of Tier 2 of the EAFM Roadmap. | ce. Continue its work to develop models that support implementation of Tier 2 of the EAFM Roadmap. -SC made progress by a) defining the features required for Tier 2 models and identifying potential advice applications, b) idntifying formal steps and operational requirements needed for Tier 2 model development, and c) examining ongoing modelling work that could support Tier 2 assessments. -Next steps towards broader implementation of Tier 2 include a) developing a triage procedure for identifying priorities for model development, and b) developing mechanisms to promote the engagement of the broader research community in Tier 2 model development. -Exploration of the multispecies Flemish Cap model for the implementation of Tier 2 is an obvious next step. | Mariano Koen-Alonso (coordination), Alfonso Pérez-Rodriguez (maybe) | Support for Tier 2 development | Progress on Tier 2 development and implementation will required additional capacity. Current capacity within WGESA and SC is limited, and getting smaller. At present, there is no capacity in SC to engage fully on Tier 2 development,
Catch and Bycatch reporting Input to WG-BDS | Request #11 The Commission requests Scientific Council, jointly with the Secretariat, to conduct ongoing analysis of the Flemish Cap cod fishery data by 2022 in order to: a. monitor the consequences of the management decisions (including the analysis of the redistribution of the fishing effort along the year and its potential effects on ecosystems, the variation of the cod catch composition in lengths/ages, and the bycatch levels of other fish species, benthos in general, and VME taxa in particular), and b. carry out any additional monitoring that would be required, including Div. 3M cod caught as bycatch in other fisheries during the closed period. | SC agreed to postpone this analysis until two years of logbook data are available and proposes monitoring the consequences of management decisions every two years. Therefore this request should be included in AM 2013 (to be conducted in 2024) | Irene Garrido, Diana Gonzalez Troncoso, Fernando Gonzalez | Haul by haul data will be provided by the Secretariat and samples (catch and length distributions) from the CPs. Problems detected in the logbook data to monitor bycatch levels of benthos.
Monitoring +A38 | Ongoing annual SC work | Survey planning, participation in surveys, data collection, dissemination, analysis, interpretation and report writing for SC. Each year for 7 + fisheries surveys as well as a number of oceanographic surveys, and dedicated benthic surveys. CPs plan, conduct surveys, analyse survey data, write, and present survey reports. | Rick Rideout, Ricardo Alpoim, Fernando González and Diana Gonzalez Troncoso
| Feeds into a number of requests including ecosystem summary sheet (ESS) | STACFEN reporting on on physical and biological variables | chair is Miguel, DEs and David Belanger, Fred Cyr, US oceanographer
Workplanning, corporate, administrative (across all components) | Request#8 The Commission requests Scientific Council to continue to develop a 3-5 year work plan, which reflects requests arising from the 2021 Annual Meeting, other multi-year stock assessments and other scientific inquiries already planned for the near future. The work plan should identify what resources are necessary to successfully address these issues, gaps in current resources to meet those needs and proposed prioritization by the Scientific Council of upcoming work based on those gaps. | Timing: Should be updated twice a year, in June and September. Discussion for September update needs at least draft Commission Requests which tend to come the last day of the Commission meeting. To build into the wprkplanning following the Commission meeting. SC have not recently had opportunity for review of Commission approved requests. | Adolfo Merino Kathy Sosebee Tom Blasdale Martha Krohn | no additional resources needed
| STACPUB | Autofillable SCR and STACFIS templates | Rick Rideout, chair Paul Regular DE